## WATMS Backlog
work item type | title 1 | title 3 | title 4 | state | estimate
Epic | Wildlife Observation Management |  |  | New
User Story | Wildlife Observation Management | Record wildlife observation |  | New | 5
Task | Wildlife Observation Management | Record wildlife observation | Design observation data model | New | 3
Task | Wildlife Observation Management | Record wildlife observation | Create mobile observation form UI | New | 5
Task | Wildlife Observation Management | Record wildlife observation | Implement photo & video upload | New | 4
Epic | Offline Data Collection & Sync |  |  | New
User Story | Offline Data Collection & Sync | Offline observation entry |  | New | 8
Task | Offline Data Collection & Sync | Offline observation entry | Implement local mobile storage | New | 5
Task | Offline Data Collection & Sync | Offline observation entry | Auto-sync when connection restored | New | 5
Epic | IoT Device Integration |  |  | New
User Story | IoT Device Integration | Ingest IoT tracking data |  | New | 8
Task | IoT Device Integration | Ingest IoT tracking data | Create IoT ingestion API | New | 5
Task | IoT Device Integration | Ingest IoT tracking data | Store GPS & sensor data | New | 3